## Sheet1
GANTT CHART TEMPLATE
| PROJECT TITLE | AI-driven PE-design for next-gen lithography
| TEAM MEMBERS | Atakan Kumas, Chris Hogendoorn, Yuhao Shan, Zijian Dong
Break
| Deadlines | Deadlines
Group meeting days
Supervisor meeting days
[5 empty] | Academic schedule: Quarters |  | Quarter 3 | [34 empty] | Quarter 3 exams | [13 empty] | Quarter 4
[5 empty] | Academic schedule: Weeks |  | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10
WBS NUMBER | TASK/MILESTONE | RESPONSIBILITY | START DATE (dd/mm/yy) | DUE DATE (mm/dd/yy) | DURATION (IN DAYS) | STATUS (%) | WEEK 0 (2/3 - 8/3) | [6 empty] | WEEK 1 (9/3 - 15/3) | [6 empty] | WEEK 2 (16/3 - 22/3) | [6 empty] | WEEK 3 (23/3 - 29/3) | [6 empty] | WEEK 4 (30/3 - 5/4) | [6 empty] | WEEK 4a (6/4 - 12/4) | [6 empty] | WEEK 4b (13/4 - 19/4) | [6 empty] | WEEK 5 (20/4 - 26/4) | [6 empty] | WEEK 6 (27/4 - 3/5) | [6 empty] | WEEK 7 (4/5 - 10/5) | [6 empty] | WEEK 8 (11/5 - 17/5) | [6 empty] | WEEK 9 (18/5 - 24/5) | [6 empty] | WEEK 10 (25/5 - 31/5) | [6 empty] | WEEK 11 (1/6 - 7/6) | [6 empty] | WEEK 12 (1/6- 31/5) | [6 empty] | (25/5 - 31/5) | [6 empty] | (25/5 - 31/5)
[7 empty] | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su | M | Tue | W | Thu | F | Sa | Su
1 | Literature review and process research | [5 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 27 | 28 | 29 | 30 | 31
1.1 | Getting familiar with Power electronics | ALL | 2026-03-02 | 2026-03-15 | 13 | 100% | bar: WEEK 0 (2/3 - 8/3) M 2 to WEEK 1 (9/3 - 15/3) Su 15
1.2 | State-of-the-art learning methods research | Atakan, Zijian | 2026-03-06 | 2026-03-15 | 9 | 100% | bar: WEEK 0 (2/3 - 8/3) F 6 to WEEK 1 (9/3 - 15/3) Su 15
1.3 | Existing approaches research | Chris, Yuhao | 2026-03-06 | 2026-03-15 | 9 | 100% | bar: WEEK 0 (2/3 - 8/3) F 6 to WEEK 1 (9/3 - 15/3) Su 15
1.4 | Reward function analysis | Chris | 2026-03-10 | 2026-03-15 | 5 | 100% | bar: WEEK 1 (9/3 - 15/3) Tue 10 to WEEK 1 (9/3 - 15/3) Su 15
1.5 | Simulation engine analysis | Atakan | 2026-03-10 | 2026-03-15 | 5 | 100% | bar: WEEK 1 (9/3 - 15/3) Tue 10 to WEEK 1 (9/3 - 15/3) Su 15
1.6 | LLM selection research | Yuhao | 2026-03-10 | 2026-03-15 | 5 | 100% | bar: WEEK 1 (9/3 - 15/3) Tue 10 to WEEK 1 (9/3 - 15/3) Su 15
1.7 | Build environment research | Zijian | 2026-03-10 | 2026-03-15 | 5 | 100% | bar: WEEK 1 (9/3 - 15/3) Tue 10 to WEEK 1 (9/3 - 15/3) Su 15
1.8 | Methodology selection (M1) | ALL | 2026-03-15 | 2026-03-15 | 0 | 100% | bar: WEEK 1 (9/3 - 15/3) Su 15
2 | Data generation and simulation processing | bar: WEEK 0 (2/3 - 8/3) M 2 to WEEK 4 (30/3 - 5/4) Su 5; WEEK 5 (20/4 - 26/4) M 20 to (25/5 - 31/5) M 15
2.1 | LLM topology generation module | Yuhao | 2026-03-16 | 2026-03-26 | 10 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 3 (23/3 - 29/3) Thu 26
2.2 | Validation algorithm design | Atakan | 2026-03-16 | 2026-03-26 | 10 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 3 (23/3 - 29/3) Thu 26
2.3 | Simulation interface development | Atakan | 2026-03-16 | 2026-03-26 | 10 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 3 (23/3 - 29/3) Thu 26
2.4 | Reward function implementation | Chris | 2026-03-16 | 2026-03-26 | 10 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 3 (23/3 - 29/3) Thu 26
2.5 | Dataset generation | Chris | 2026-03-16 | 2026-03-31 | 15 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 4 (30/3 - 5/4) M 30
2.6 | RL framework design | Zijian | 2026-03-16 | 2026-03-31 | 15 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 4 (30/3 - 5/4) M 30
2.7 | End-to-end pipeline integration | Atakan | 2026-03-16 | 2026-03-31 | 15 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 4 (30/3 - 5/4) M 30
2.8 | HPC / LTSpice deployment | Atakan | 2026-03-16 | 2026-03-30 | 14 | 100% | bar: WEEK 2 (16/3 - 22/3) M 16 to WEEK 4 (30/3 - 5/4) M 30
2.9 | End-to-end pipeline completed (M2) | ALL | 2026-03-23 | 2026-03-30 | 7 | 100% | bar: WEEK 3 (23/3 - 29/3) M 23 to WEEK 4 (30/3 - 5/4) M 30
2.1.0 | Mid-Term Presentation | ALL | 2026-03-31 | 2026-03-31 | 1 | 100%
2.11 | Planning Next Phase | ALL | 2026-04-01 | 2026-04-05 | 7 | 100% | bar: WEEK 4 (30/3 - 5/4) W 1 to WEEK 4 (30/3 - 5/4) Su 5
3 | Model training and tuning | bar: WEEK 0 (2/3 - 8/3) M 2 to WEEK 4 (30/3 - 5/4) Su 5; WEEK 5 (20/4 - 26/4) M 20 to (25/5 - 31/5) M 15
3.1 | SFT dataset construction | Yuhao | 2026-04-20 | 2026-04-27 | 7 | 100% | bar: WEEK 5 (20/4 - 26/4) M 20 to WEEK 6 (27/4 - 3/5) M 27
3.2 | SFT training(M3) | Yuhao,Atakan | 2026-04-20 | 2026-04-27 | 7 | 100% | bar: WEEK 5 (20/4 - 26/4) M 20 to WEEK 6 (27/4 - 3/5) M 27
3.3 | GRPO training framework | Zijian,Yuhao,Chris | 2026-04-20 | 2026-05-11 | 21 | 100% | WEEK 4a (6/4 - 12/4) F 10: Suffering
3.4 | RL training loop integration (M4) | Zijian,Atakan | 2026-04-27 | 2026-05-18 | 21 | 100% | bar: WEEK 6 (27/4 - 3/5) M 27 to WEEK 8 (11/5 - 17/5) M 11
3.5 | Tree-search strategy design | Chris | 2026-04-27 | 2026-05-11 | 14 | 100% | bar: WEEK 6 (27/4 - 3/5) M 27 to WEEK 8 (11/5 - 17/5) M 11
3.6 | Benchmarking and hyperparameter tuning | Atakan | 2026-04-27 | 2026-05-11 | 14 | 100% | bar: WEEK 6 (27/4 - 3/5) M 27 to WEEK 8 (11/5 - 17/5) M 11
3.7 | SFT model trained | Yuhao,Atakan,Chris | 2026-05-11 | 2026-05-18 | 7 | 100% | bar: WEEK 8 (11/5 - 17/5) M 11 to WEEK 9 (18/5 - 24/5) M 18
3.8 | RL training complete (M5) | ALL | 2026-05-11 | 2026-05-18 | 7 | 100% | bar: WEEK 8 (11/5 - 17/5) M 11 to WEEK 9 (18/5 - 24/5) M 18
4 | Search Strategy Optimization | bar: WEEK 0 (2/3 - 8/3) M 2 to WEEK 4 (30/3 - 5/4) Su 5; WEEK 5 (20/4 - 26/4) M 20 to (25/5 - 31/5) M 15
4.1 | Grouped GRPO tree-search implementation | Chris, ZIjian | 2026-05-18 | 2026-05-25 | 7 | 100% | bar: WEEK 9 (18/5 - 24/5) M 18 to WEEK 10 (25/5 - 31/5) M 25
4.2 | Epsilon-greedy Top-K selection | Chris, ZIjian | 2026-05-18 | 2026-05-25 | 7 | 100% | bar: WEEK 9 (18/5 - 24/5) M 18 to WEEK 10 (25/5 - 31/5) M 25
4.3 | Duplicate topology filtering | Chris | 2026-05-18 | 2026-05-25 | 7 | 100% | bar: WEEK 9 (18/5 - 24/5) M 18 to WEEK 10 (25/5 - 31/5) M 25
4.4 | RL updater optimization | Yuhao | 2026-05-18 | 2026-05-25 | 7 | 100% | bar: WEEK 9 (18/5 - 24/5) M 18 to WEEK 10 (25/5 - 31/5) M 25
4.5 | HPC Infrastructure Reconstruction | Atakan | 2026-05-11 | 2026-05-25 | 14 | 100% | bar: WEEK 8 (11/5 - 17/5) M 11 to WEEK 10 (25/5 - 31/5) M 25
4.6 | Reward function refinement | Chris | 2026-05-25 | 2026-06-01 | 7 | 100% | bar: WEEK 10 (25/5 - 31/5) M 25 to WEEK 11 (1/6 - 7/6) M 1
4.7 | Benchmarking and result analysis | Chris, Atakan, Yuhao | 2026-05-25 | 2026-06-01 | 7 | 100% | bar: WEEK 10 (25/5 - 31/5) M 25 to WEEK 11 (1/6 - 7/6) M 1
4.8 | Curriculum constraint scheduling | Atakan,Chris | 2026-05-25 | 2026-06-01 | 7 | 100% | bar: WEEK 10 (25/5 - 31/5) M 25 to WEEK 11 (1/6 - 7/6) M 1
4.9 | GUI implementation | Atakan | 2026-05-25 | 2026-06-01 | 7 | 100% | bar: WEEK 10 (25/5 - 31/5) M 25 to WEEK 11 (1/6 - 7/6) M 1
4.1 | Optimized search framework (M6) | ALL | 2026-05-25 | 2026-06-01 | 7 | 100% | bar: WEEK 10 (25/5 - 31/5) M 25 to WEEK 11 (1/6 - 7/6) M 1
5 | Finalization | bar: WEEK 0 (2/3 - 8/3) M 2 to WEEK 4 (30/3 - 5/4) Su 5; WEEK 5 (20/4 - 26/4) M 20 to (25/5 - 31/5) M 15
5.1 | Result Evaluation(M7) | ALL | 2026-06-01 | 2026-06-08 | 7 | 100% | bar: WEEK 11 (1/6 - 7/6) M 1 to WEEK 12 (1/6- 31/5) M 8
5.2 | Final report submitted(M8) | ALL | 2026-06-01 | 2026-06-08 | 7 | 100% | bar: WEEK 11 (1/6 - 7/6) M 1 to WEEK 12 (1/6- 31/5) M 8
5.3 | Presentation Preparation | ALL | 2026-06-01 | 2026-06-14 | 14 | bar: WEEK 11 (1/6 - 7/6) M 1 to (25/5 - 31/5) M 15